Oct-Nov, 2025 MES Trip- Improvement Plans🡪  Results by Feb, 2026

| Site- Health Asst (HA) Local Govt (LG) | HA | Local Govt | OIHCS |
| --- | --- | --- | --- |
| Aur (Tobal) HA- James Saimon LG- Bolan Erwin | - Clean sink, floors, office; - No - Restart weekly reports- Yes - Do House-to-house case finding for < 5yo Children and NCD patients; No - Make Community Profile and post in clinic No - Post clinic hours on front door- N0 | - Meet with health assistant at least one time per month to supervise and work on improvements (or invite him to Local Council or Health Council meetings) - Yes - Hook up water supply; No - Set Hours of clinic operation for health assistant to open- Yes - Provide SSB radio -No | - Plan on-site missions to initiate NCD PEN and Immunization delivery by health assistant- No |
| Mejit HA- Joel Laidron LG- Neal Keju | - Organize meds and supplies- Yes - House-to-house Case Finding Survey for NCD patients and <5yo children- No - Put NCD and < 5yo children into registry books- No | - Fix roof/gutters- No - Meet with health assistant at least one time per month to supervise and work on improvements (or invite him to Local Council or Health Council meetings)- Yes - Provide filing cabinet that can be locked- Yes | - Provide Vit A and Albendazole for School Program- Yes |
| Maleolap (Kaben) HA- Rodney Briand LG- Franko M | - House-to-house Case Finding Survey for NCD patients and <5yo children- No - Put NCD and < 5yo children into registry books -No - Post hours of operation; - Yes | 1) Provide light bulbs; No 2) lock for storage; No 3) fix regulator for solar N0 | 1) follow-up status of water pump order; Yes 2) Check if OIHCS can provide radio Yes 3) Provided registry books- Yes |
| Ailuk HA- Kori Marshall LG- Redner Alfred | - Do Case finding, -No - Put case finding NCD patients and < 5yo children into registry books with return visit dates to use for follow-up of patients- No - Clean exam rooms; - Yes - Organize meds and supplies Yes | - Meet with health assistant at least one time per month to supervise and work on improvements (or invite him to Local Council or Health Council meetings) - Yes - fix electricity, Yes - fix roof leaks.NA - Provide lock for storage room- No | - Meeting with Heroko to support School Program- Yes - Provided registry books- YEs |
| Wotje HA- Jakin Robert LG- Bijen Hax | - Do House-to-House Case finding- No - Put case finding NCD patients and NCD patients and < 5yo children into registry books with return visit dates use for follow-up of patients No - Make Community profile and post in clinic- No - clean bathrooms- No - Establish safe disposal of sharps - Yes | - Clean and paint doors- No - Fix loose roof tins- No - Split water supply (well🡪 toilets; rain🡪 sinks)- No | - Provide registry books- Yes - Arrange with Aqua to fix gutters, rain catchment- Yes |
| Likiep HA- Brandy Kemlan LG-Nicky deBrum | - Clean floors, bathrooms- Yes - Start school program- No - Community profile- No - Do House-to-house Case finding for children < 5yo and NCD patients - No - Create registry books for NCD and children < 5yo with return visit dates to use for outreach | - Repair leak in roof- No Install pump, fix toilet (no lever; water not connected)- No - Provide batteries, connect electricity- No - Meet with health assistant at least one time per month to supervise and work on - improvements (or invite him to Local Council or Health Council meetings)- No | - Recommend for Timesheets to be submitted by Local Government- Yes - Inform Mayor (Nikki deBrum) of MLT decisions- Yes - Check fees charged by HA for services ($2 visit; $2.50 emerg)- clarify policy- No - Generator- provided by OIHCS vs HA? - Yes |
| Wotho HA- Banner Aister LG- Banner Joseph | - Keep line list of outpatients seen in clinic-No - Discard sharps safely (in burn pit)- empty sharps container when ¾ full- Yes - Keep toilet and toilet area very clean- Yes - Get rid of mice and rats- Yes - Unpack meds from boxes, organize them on shelves- No - Start community health promotion activities (and keep record of these)- No | - Meet with health assistant at least one time per month to supervise and work on improvements (or invite him to Local Council or Health Council meetings)- Yes - Replace door knobs in health center- No | - Send team for 1 week to assist with case finding, set-up of patient registries, training for vaccinations and NCD PEN care- No - Repair electrical system (need battery and regulator)- Yes - Replace SSB radio- No - Fix gutters- Yes - Fix water supply including pump- No |
| Ujae HA-Merina Riketa LG- Misao Bokin | - Post clinic hours outside of health center- Yes - Set up and use registry books for NCD, Children < 5yo Antenatal, family planning- No (partly done but not yet finished) | - Meet with health assistant at least one time per month to supervise and work on improvements (or invite him to Local Council or Health Council meetings)- Yes - Fix roof leak- No | - Replace doors (3) and door knobs (7)- No - Repair electrical system- Yes - Provide Starlink- Yes - Fix water connections to health center- No |
| Ebon (Toka)- No f/u visit made in Feb. | - Clean floors, bathrooms - Start school program - Community Profile - Do House-to-house Case finding for children < 5yo and NCD patients - Make and use registries for NCD, Children < 5yo, Antenatal and Family Planning with return visit dates to use for outreach - Unpack meds from boxes, organize them on shelves - Post clinic hours outside the front door of health center | - Provide Light pulps (5) - 1 Door - 4 Door knobs - Glue for wall bottom frame - Glass holder louvers frame 3 sets (5x) and 2 sets (5x) - Monitoring and work with the HA at least a month | - Fix electrical system (including solar panel/Electricity |
| Lae HA-Akji Langbata LG- Swinev Langrine | - Keep line list of outpatients seen in clinic- No - Community Profile - Yes - Post clinic hours outside health center- Yes - Complete case finding for NCD, Children< 5yo and add to registry books (include return visits)- No - Make and use registries for NCD, Children < 5yo, Antenatal and Family Planning with return visit dates to use for outreach- No | - Consider making health council (or can continue to meet quarterly with HA)- Yes - Fix minor problems with the wall crack and roof - No (yes walls, no roof) - 3 Doors (1 for pharmacy and 2 for bathrooms)- No | - Fix electrical system (including solar panel/Electricity- Yes - Ship Starlink (HA can install)- Yes - Ship water pump, UNICEF- No - Provide cold chain- No - Transport (Motor bike)- No |
| Namu (Majkin) HA-Oktan Timothy LG- Misao Bokin | - Improve registries for NCD, Well Child, School- No - Community profile and case finding- No - Unpack boxes, organize meds on shelves- Yes - Post clinical hours- Yes | - Local council- Meet with health assistant at least one time per month to supervise and work on improvements- Yes - Replace roof nails- No - Order and fix floor tiles- No | - Fix electricity to health center- Yes - Water pump– No - Starlink to install- Yes |
| Alinglaplap (Woja) HA-Weston Ejli LG- Ishmael Rang | - Make registries with all NCD patients and another for <5yo children Yes (still needs WCC) - Use registries to identify patients needing home f/u yes - Post community profile in HC Yes - Clean sink, floor and toilet Yes - Unpack boxes and organize meds on shelves Yes | - Meet with health assistant at least one time per month to supervise and work on improvements Yes - Provide 4 door frames- 2 for facility and 2 for toilet and shower No - Repair cement water catchment No | - Repair electric (two batteries needed) Yes - Improve delivery of ordered supplies Yes |
| Jabat HA- Jounran Jounran Acting Mayor- Barry Dawoj | - Start NCD and preschool child registires- No including return visits use for guiding outreach - Clean floors, toilet, sink better- Yes - Unpack boxes. Organize meds and supplies on shelves in clinic- Yes | - Meet with HA at least 1X each month to supervise, assist with community programs (like school program)- Yes - Repair cement water catchment tank- No - Fix 4 door frames (two in clinic, one in toilet, one in shower)- No | - 2 Batteries needed- 1 for cold box and one for general electricity- Yes - Check if we can provide substitute HA when we transfer Juaran to Alinglaplap coverage - Yes |
| Jaluit (Jabor) HA- Elmon Mouch LG- Tieg Wonne | - Clear out boxes in front of ER door- No - Better cleaning of toilet and HC rooms- Yes - Do school program ASAP - No - Fix floors when floor tiles provided- NA | - Replace emergency door-No - Request to replace broken door in Imroj HC- No - Prepare living space for Nurse Practitioner-No - Meet with health assistants at least one time per month to supervise and work on improvements (Create health council or invite HA to municipal council meetings)- No | - Stand by to assist local government to exercise supervision of HA- NA - Request new sink table top- No - Starlink replacement or renew V-Sat- Yes (starlink) - Provide floor tiles & Glue- NA - Dental Chair - No - Front window- No - Provide Window screens- No - Patient bed (3)- Yes - Bicycle for Imiej (request 2 for council and HA)- No - Paint Imroj (2 gal inter; 2 gal exterior)- No - Aircon units (2 clinic; 2 accomodation)- No - Swat team for PEN, WCC, ANC, Case finding/registries- No |
| Namrik HA- Harris Harris LG- Ringo | - Add return visit to NCD register and use for follow-up of patients- No - Make registry for <5yo and use for follow-up of children- No - Order Vit A and Albendazole and do school program including physical exam, as soon as possible- Yes - Clean out junk boxes, sink, around windows, clean doors- No - Use new antenatal care forms- NA - Order pregnancy wheel, measuring tape for prenatal care- ? | - Meet with health assistant at least one time per month to supervise and work on improvements- No - Provide two doors (bathroom, pharmacy) and 6 door knobs in clinic - No | - Provide water pump- No - Provide SSB radio- No - Solar system for electricity - Yes |
| Ebon (Ebon) HA- Kojen Koneillis LG-Rijino Jibas | - Cleaning walls, doors, window sills, counters, shelves- Yes - Maintain cold box (instructions on lid). Monitor temp in logbook- No - Organize meds and discard expired, including vaccines- Yes - School program- exam, Vit A, Albendazole for every child- record on school roster- Yes | - Meet with health assistant at least one time per month to supervise and work on improvements- No | - Provide batteries for solar system🡪Yes |
| Mili (Enejit) HA-Ruth Andrew LG- none present | 1) No plan because no acting Mayor present. |  | 1) Convene planning meeting with Acting Mayor and HA- No |
| Arno (Inne) HA-Jally Enos LG- Bokedrikdrik Keju | 1) Upack boxes - do not store on floor🡪 Yes 2) Order supplies needed from OIDS (doppler, measuring tape for ANC, Infant weight scale, scale, pulse oximeter, Pregnancy wheel, laciration set, OB delivery pack🡪 Yes 3) Restart school program including Vit A, Deworm and physical exam🡪 No 4) Start registries for NCD and children less than 5 yo with return visit column - use to guide outreach🡪 No | 1) Need with the HA every month to supervise, check clinic hours and help organize community advance like school program etc.--> Yes 2) Replace termite cabinet 🡪 No | 1) None |
| Lib HA- Joe Naka LG- Richard Jajo | 1) Follow local government directions for improvement→ Yes | 1) Local govt to supervise HA closely- to work on multiple improvement items and bring up performance score→ Yes | 1) Stand by to assist local government to exercise supervision of HA→ Yes |
| Total | 30/65= 46% | 14/46= 30% | 28/50= 56% |